## User Stories
Story ID | Epic | User Story | Business Value | Priority | Acceptance Criteria | Status
US-001 | Executive Dashboard | As a Business Leader, I want to view total sales, profit, orders and profit margin so that I can quickly understand overall business performance. | Provides a single executive view of core KPIs. | High | 1. Total Sales is displayed correctly. 2. Total Profit is displayed correctly. 3. Total Orders is displayed correctly. 4. Profit Margin is calculated correctly. 5. KPIs reconcile with validated source data. | To Do
US-002 | Sales Trend | As a Sales Manager, I want to view monthly sales and profit trends so that I can identify growth and decline periods. | Supports trend monitoring and planning. | High | 1. Monthly trend is displayed. 2. Sales and profit can be compared. 3. Date filtering works. 4. Values reconcile with SQL results. | To Do
US-003 | Regional Analysis | As a Regional Manager, I want to compare sales and profit by region and state so that I can identify high- and low-performing markets. | Supports regional performance decisions. | High | 1. Region-level sales is available. 2. State-level drill-down is available. 3. Profit is visible. 4. Ranking is accurate. | To Do
US-004 | Product Analysis | As a Product Manager, I want to identify top and underperforming products so that I can improve product and inventory decisions. | Highlights products driving or reducing performance. | High | 1. Products can be ranked by sales. 2. Products can be ranked by profit. 3. Category filtering works. 4. Top and bottom products are identifiable. | To Do
US-005 | Customer Analysis | As a Sales Manager, I want to identify high-value customers so that I can focus retention and sales activities. | Supports customer prioritization. | Medium | 1. Customers can be ranked by sales. 2. Profit contribution is available. 3. Order count is available. 4. Customer filters work. | To Do
US-006 | Data Quality | As a Business Analyst, I want source data to be cleaned and validated so that reports contain reliable information. | Improves trust in analytical outputs. | High | 1. Missing values are assessed. 2. Duplicate records are checked. 3. Data types are validated. 4. Key fields are checked before reporting. | To Do
US-007 | SQL Validation | As a Business Analyst, I want dashboard KPIs to be reconciled against SQL results so that reporting figures are accurate. | Reduces KPI discrepancies. | High | 1. KPI SQL queries are documented. 2. Power BI values are compared with SQL. 3. Differences are investigated. 4. Validation result is recorded. | To Do
US-008 | Dashboard Filters | As a Business User, I want to filter the dashboard by date, region, category and customer segment so that I can perform focused analysis. | Enables self-service analysis. | Medium | 1. Date filter works. 2. Region filter works. 3. Category filter works. 4. Customer segment filter works. 5. Visuals update consistently. | To Do
US-009 | UAT | As a Business User, I want to validate the dashboard against agreed business scenarios so that the solution is fit for use. | Ensures business acceptance before release. | High | 1. UAT scenarios are documented. 2. Expected and actual results are recorded. 3. Defects are logged. 4. Critical defects are resolved. 5. UAT sign-off is completed. | To Do
US-010 | Business Insights | As a Business Leader, I want key insights and recommendations from the analysis so that I can take data-driven actions. | Converts analysis into business decisions. | High | 1. Key findings are documented. 2. Findings are supported by data. 3. Recommendations are actionable. 4. Business impact is described. | To Do

## Agile Backlog
Backlog Order | Story ID | Epic | Priority | Status
1 | US-001 | Executive Dashboard | High | To Do
2 | US-002 | Sales Trend | High | To Do
3 | US-003 | Regional Analysis | High | To Do
4 | US-004 | Product Analysis | High | To Do
5 | US-005 | Customer Analysis | Medium | To Do
6 | US-006 | Data Quality | High | To Do
7 | US-007 | SQL Validation | High | To Do
8 | US-008 | Dashboard Filters | Medium | To Do
9 | US-009 | UAT | High | To Do
10 | US-010 | Business Insights | High | To Do