## Jira Backlog
Issue Key | Issue Type | Epic | Summary | Description | Priority | Sprint | Status | Acceptance Criteria
BA-001 | Epic | Sales Analytics | Sales & Business Performance Analytics | End-to-end analytics solution for sales, profitability, regional, product and customer analysis. | Highest | All Sprints | To Do | All project deliverables completed and validated.
BA-002 | Story | Sales Analytics | Gather business requirements | Document business problem, objectives, scope, stakeholders and KPIs. | High | Sprint 1 | Done | BRD completed and reviewed.
BA-003 | Story | Sales Analytics | Create user stories | Convert business requirements into Agile user stories and acceptance criteria. | High | Sprint 1 | Done | 10 user stories documented.
BA-004 | Task | Sales Analytics | Prepare source data | Review sales, customer and product datasets and assess data quality. | High | Sprint 1 | To Do | Required datasets identified and quality checks documented.
BA-005 | Task | Sales Analytics | Clean data using Power Query | Remove duplicates, handle missing values and standardize data types. | High | Sprint 1 | To Do | Cleaned dataset is ready for analysis.
BA-006 | Story | Sales Analytics | Perform SQL analysis | Analyze sales, profit, products, customers and regional performance using SQL. | High | Sprint 2 | To Do | Business questions answered and SQL scripts documented.
BA-007 | Task | Sales Analytics | Validate SQL KPIs | Reconcile key SQL calculations with source data. | High | Sprint 2 | To Do | Sales, profit and order metrics pass validation.
BA-008 | Story | Sales Analytics | Build Power BI dashboard | Create data model, measures, KPIs and interactive visuals. | High | Sprint 3 | To Do | Dashboard meets agreed requirements and filters work.
BA-009 | Task | Sales Analytics | Validate Power BI dashboard | Compare Power BI KPIs against SQL results. | High | Sprint 3 | To Do | No unexplained KPI discrepancies.
BA-010 | Story | Sales Analytics | Execute UAT | Validate dashboard using business scenarios and expected results. | High | Sprint 4 | To Do | UAT cases executed and results recorded.
BA-011 | Bug | Sales Analytics | Resolve UAT defects | Log, investigate, fix and retest defects found during UAT. | High | Sprint 4 | To Do | Critical defects closed or formally accepted.
BA-012 | Task | Sales Analytics | Business sign-off | Obtain simulated business acceptance after successful UAT. | High | Sprint 4 | To Do | UAT sign-off documented.
BA-013 | Story | Sales Analytics | Document insights and recommendations | Translate analytical findings into actionable business recommendations. | Medium | Sprint 4 | To Do | Insights are supported by data and recommendations are actionable.
BA-014 | Task | Sales Analytics | Prepare portfolio documentation | Organize BRD, backlog, SQL, Excel, Power BI, UAT and insights artifacts. | Medium | Sprint 4 | To Do | GitHub project is complete and easy to navigate.

## Sprint Plan
Sprint | Focus | Planned Work | Expected Outcome
Sprint 1 | Requirements & Data Preparation | BRD, user stories, stakeholder analysis, dataset review, Power Query cleaning | Approved requirements and analysis-ready data
Sprint 2 | SQL & Data Analysis | SQL queries, KPI calculations, business analysis and validation | Validated analytical results
Sprint 3 | Power BI Development | Data model, DAX measures, dashboard pages, filters and KPI validation | Functional Power BI dashboard
Sprint 4 | UAT & Release | UAT, defect management, sign-off, insights and portfolio documentation | Validated solution and completed portfolio

## Workflow
Workflow Stage | Meaning
To Do | Work is planned but not started.
In Progress | Work is actively being completed.
Testing | Work is complete and undergoing validation/UAT.
Done | Acceptance criteria are met and the work is completed.